## CoverPage (hidden)
PAYMENT CERTIFICATE | [5 empty] | 4
INTERIM CERTIFICATE
| Main Contractor: - |  |  |  |  | Services supplied to: -
| Mabona Civils & Plant Hire |  |  |  |  | OR Tambo District Municipality
| Goso Location |  |  |  |  | Water Service Department
| Mnceba A/A |  |  |  |  | Private Bag X 6043
| Mt Ayliff |  |  |  |  | Mthatha
| 4735 |  |  |  |  | 5100
| Vat No.: 4850255722 |  |  |  |  | Vat No.: 4520156896
CONTRACT INFORMATION
| PROJECT NAME |  | Dumasi Regional Water Supply Phase 1
| CONTRACT NO. |  | MIS 316 080 D
| ENGINEER |  | Ziinzame Consulting Engineers (Pty) Ltd
REQUIRED INFORMATION FROM THE CONTRACTOR
| VAT REG. Nº |  | 4850255722
| CERTIFICATE Nº |  | 4
| DATE |  | 2023-08-16
| ITEMS | [5 empty] | AMOUNT
| Contract Price (Excl. VAT) | [5 empty] | 32347826.0843 | 32347826.0843 | 0
| Variation Approved (Excl. VAT) | [5 empty] | 0 | 0 | 0
| Adjusted Contract Price (Excl. VAT) | [5 empty] | 32347826.0843 | 32347826.0843 | 0
0
| Work done to date (Excl. VAT) | [5 empty] | #REF! | 2202966.6667 | #REF!
| Add VO | [5 empty] | 0 | 0 | 0
| ADD CLAIMS | [5 empty] | 0 | 0 | 0
| Sub Total | [5 empty] | #REF! | 3018966.6667 | #REF!
| Less Retention of 10%: To a maximum 5% of |  |  | 32347826.0843 | 1617391.3042 |  | #REF! | 359509.1667 | #REF!
| Less Guarantee of 10%: | [5 empty] | 0 | 0 | 0
| Less Penalties | [5 empty] | 0 | 0 | 0
| Add 80% of Materials on site | [5 empty] | 273360 | 816000 | -542640
| Sub Total | [5 empty] | #REF! | 2717070 | #REF!
| Less Previous Payments | [5 empty] | 3235582.5 | 1170675 | 2064907.5
| Amount Due | [5 empty] | #REF! | 1546395 | #REF!
| Add VAT @ 15% | [5 empty] | #REF! | 231959.25 | #REF!
| Less Cession Amount (VAT Inclusive) | [5 empty] | 0 | 0 | 0
| Add interest | [5 empty] | 0 | 0 | 0
| TOTAL AMOUNT DUE | [5 empty] | #REF! | 1778354.25 | #REF!
| Contract Price (Incl. VAT)+(Escalations) |  |  | 37199999.997
| Less expenditure to date incl. this claim (Incl. VAT) |  |  | #REF! |  |  |  |  | #REF!
| Less 10% retention (Incl. VAT) |  |  | #REF!
| Less guarantee (Incl. VAT) |  |  | 0
| Balance of Funds |  |  | #REF!
| % of Expenditure to date |  |  | #REF!
| % of Physical Progress to date |  |  | 22%
I declare that the abovementioned payment is approved in accordance with the conditions of contract and that the work to the value of the amount has been completed.
|  | CONTRACTOR |  | CONSULTING |  | CLIENT
|  | Mabona Civils & Plant Hire |  | Ziinzame Consulting Engineers (Pty) Ltd |  | ORTDM
| Date: | 2023-08-16 |  | 2023-08-16
M. NDABANKULU, PrEng
Name:
Signature:

## M.O.S (hidden)
Dumasi Regional Water Supply Phase 1: Contract 04
MATERIALS ON SITE
ITEM NO IN | DESCRIPTION |  | UNIT | QUANTITY | RATE | VALUE MATERIALS
SCHEDULE |  |  |  |  | ALLOWED | ON SITE
IPC #1 |  |  | No. |  | 0 | 0
IPC#2 | 315mm mPVC pipe 6m length |  | No. | 67 | 5100 | 341700
IPC#3 |  |  | No. |  | 0 | 0
270
TOTAL VALUE OF MATERIALS ON SITE | [5 empty] | 341700
DEDUCT 20% OF TOTAL VALUE OF MATERIALS ON SITE | [5 empty] | 68340 |  | 273360
AMOUNT PAYABLE FOR MATERIALS ON SITE | [5 empty] | 273360

## Revised Sumary
AMATHOLE DISTRICT MUNICIPALITY
Centane Water Supply Phase 4: Contract 01
SUMMARY OF SECTIONS
SECTION | DESCRIPTION | BILLED AMOUNT (RAND)
1 | PRELIMINARY AND GENERAL |  | #DIV/0!
2 | GRAVITY LINE
NETT TOTAL TENDER (VAT EXCLUDED)
ADD 15% VAT
TOTAL (VAT INCL.)

## P&G - Section 1
AMATHOLE DISTRICT MUNICIPALITY
Centane Phase 4 Contract 1
ITEM REF | PAYMENT | DESCRIPTION | UNIT | BILLED QTY | RATE | BILLED AMOUNT
1 | SABS 1200 A | SABS 1200 A - GENERAL
1.1 | 8.3 | FIXED-CHARGE AND VALUE RELATED ITEMS
1.1.1 | 8.3.1 | Contractual Requirements | Sum | 1
| 8.3.2.2 | Facilities for Contractor
1.1.5 |  | a) Offices and storage sheds | Sum | 1
1.1.8 |  | d) Living accommodation | Sum | 0
1.1.9 |  | e) Ablution and latrine facilities | Sum | 1
1.1.10 |  | f) Tools and equipment | Sum | 1
1.1.11 |  | g) Water supplies, electric power and communications | Sum | 1
1.1.12 |  | h) Dealing with water (see 5.5) | Sum | 1
1.1.13 |  | i) Access (see 5.8) | Sum | 1
1.1.14 |  | j) Plant | Sum | 1
1.1.16 | 8.3.4 | Removal of Site Establishment | Sum | 1
| PSA 8.4.6 | Compliance with the OHS Act (1993, as amended), the Construction Regulations (2014) and the Particular Safety Specification:
1.1.18 | PSHSS 6.1.2; CR 5(1)(l) | i) Preparation of the Contractor's site specific Health and Safety Plan | Sum | 1
| GSR 2; PSHSS 7.7 | iii) Provision of SABS Personal Protective Equipment
1.1.20 |  | (a) Hard Hats | No | 8
1.1.21 |  | (b) Reflective vests | No | 8
1.1.22 |  | (c) Protective foot wear | No | 8
1.1.23 |  | (d) Corded Earplugs | No | 0
1.1.24 |  | (e) Dust masks FFP2 | No | 50
1.1.25 |  | (g) Gloves | No | 10
1.1.26 |  | (h) Goggles | No | 10
| CR 7(1)(g); | iv) Cost of medical certificates and medical surveillance
1.1.27 | PSHSS 7.2 | (a) Initial (baseline) medical examinations | No | 8
1.1.28 |  | (b) Exit medical examinations | No | 8
1.1.34 | PSA 8.4.7 | Compliance with EMP and EMPr | Sum | 1
1.2 | 8.4 | TIME-RELATED ITEMS
1.2.1 | 8.4.1 | Contractual Requirements | Sum | 1
| 8.4.2 | Operation and Maintenance of Facilities on Site, for Duration of Construction, except where otherwise stated
| 8.4.2.1 | Facilities for Engineer
1.2.2 |  | a) Furnished offices (1No.) | Sum | 1
1.2.3 | PSAB 8.4.1 | b) Telephone | Sum | 1
1.2.4 |  | c) Nameboards (2 No.) | Sum | 1
1.2.5 |  | d) Survey assistants and materials | Sum | 1
| 8.4.2.2 | Facilities for Contractor
1.2.6 |  | a) Offices and storage sheds | Sum | 1
1.2.17 | 8.4,5 | Other Time- Related Obligations | Sum | 1
| PSA 8.4.6 | Compliance with the OHS Act (1993, as amended), the Construction Regulations (2014) and the Particular Safety Specification:
1.2.18 | CR 5(1)(g) | i) Contractor's time related obligations in respect of the Occupational Health and Safety Act and Construction Regulations | month | 2
1.2.19 | CR 8(5); PSHSS 6.1.5 | ii) Provision of a full- time SACPCMP registered Construction Health and Safety Officer | month | 0
1.2.20 |  | iii) Provision of a part-time assistant SACPCMP Candidate Construction Health and Safety Officer for Subcontractor Management & Assistance | month
1.2.35 | CR 7(1)(c)(e) | viii) Submission of a Health and Safety File | Sum | 1
1.2.36 | PSA 8.4.7 | Compliance with EMP and EMPr | Sum | 1
Total Carried Forward To Summary

## GRAVITY LINE
AMATHOLE DISTRICT MUNICIPALITY
Centane Phase 4 Contract 1
ITEM REF | PAYMENT | DESCRIPTION | UNIT | BILLED QTY | RATE | BILLED AMOUNT
4J |  | SECTION 4J: BULK GRAVITY MAIN (ELV T1 - Existing Reservoir)
EXCAVATION (PIPE TRENCHES)
4J.1 | SANS 1200C | SITE CLEARANCE
| 8.2.1 | Clear and grub vegetation and trees of girth up to 1m.
4J.1.1 |  | 3m wide | m | 1370
| 8.2.2 | Remove and grub large trees and tree stumps of grith
4J.1.2 |  | Over 1,0m and up to 2,0m | No. | 2
4J.1.3 |  | Over 2,0m and up to 3,0m | No. | 2
4J.1.4 | 8.2.5 | Take down existing fences and reinstate | m | 50
4J.1.5 | 8.2.10 | Remove topsoil to nominal depth of 150mm and stockpile and maintain and replace after compaction | m² | 206
Total Carried Forward
Brought forward
4J.2 | SANS 1200DB PSDB 8.5 | TRENCH EXCAVATION
| 8.3.2(a) | Excavate by machine with labour assisted backfill Excavate in all materials for trenches,backfill,compact and dispose of surplus/unsuitable material. For pipes up to 110mm dia, for depths:
4J.2.1 |  | up to 1,5m | m | 1370
4J.2.2 |  | Over 1,5m and up to 2,5m | m | 0
4J.2.3 |  | Over 2,5m and up to 3,5m | m | 0
For DUAL pipe trenches for pipe up to 110mm diameter with 200m mdistance between pipes, for depths
4J.2.4 |  | up to 1,5m | m | 300
4J.2.5 |  | Over 1,5m and up to 2,5m | m | 150
4J.2.6 |  | Over 2,5m and up to 3,5m | m | 0
2.8
| SANS 1200DB 8.3.2(b) | Extra-over 8.3.2(a) items for (prov):
4J.2.7 |  | Hard rock excavations | m³ | 20
4J.2.8 | 8.3.2(c) | Excavate and dispose of unsuitable material from trench bottom within 5km radius | m³ | 20
| 8.3.3 | EXCAVATION ANCILLARIES
| 8.3.3.1 | Make up deficiency in backfill material (Provisonal)
4J.2.9 |  | From other excavations on site | m³ | 50
4J.2.10 |  | By importation from designated borrow pits | m³ | 20
4J.2.11 | 8.3.3.3 | Compaction in road reserves | m³ | 20
PARTICULAR ITEMS
Existing Services that Intersect or Adjoin a Pipe Trench
Note: Searching and exposing of existing services, where instructed by
the Engineer, will be done and paid as Dayworks.
Services that intersect a trench
4J.2.12 |  | Electical cables (overhead and underground) | No. | 3
b) Services that adjoin a trench
4J.2.13 |  | Electical cables (overhead and underground) | m | 15
| 8.3.6 | FINISHING
Reinstate road surfaces
4J.2.14 |  | a) Gravel on shoulders | m² | 50
4J.2.15 |  | d) Gravel wearing course in roadway | m² | 12
Total Carried Forward
Brought forward
4J.3 | SANS 1200 LB | BEDDING
| 8.2.1 | Provision of bedding from trench excavation within 0.5km
4J.3.1 | 8.2.1 a) | Selected granular material | m³ | 89
4J.3.2 | 8.2.1 b) | Selected fill material | m³ | 309
| SANS 1200LB 8.2.2 | Provision of bedding by importation
| 8.2.2.1 | From other necessary excavations within 0.5km (Provisional)
4J.3.3 |  | a) Selected granular material | m³ | 30
4J.3.4 |  | b) Selected fill material | m³ | 30
| 8.2.2.3 | From commercial sources (Provisional)
4J.3.5 |  | a) Selected granular material | m³ | 20
4J.3.6 |  | b) Selected fill material | m³ | 30
4J.3.7 | 8.2.4 | Encasing pipes in 25 MPa/19mm concrete for pipes up to 110mm | m³ | 2
diameter.
Total Carried Forward
Brought forward
4J.4 | SANS 1200L | MEDIUM-PRESSURE PIPELINES
| PSL 8.1 | Supply, lay, bed, disinfect and test pipes for domestic water supply on
flexible pipe bedding complete with couplings
uPVC Pipes
4J.4.1 |  | 75mm diam. Class 12 | m | 1370
SPECIALS AND FITTINGS
| 8.2.2 | Extra-Over 4J4 for supplying, laying and bedding and testing of
specials complete with couplings
uPVC pipe bends class 12 for:
4J.4.3 |  | 75 mm dia x 90º | No. | 1
4J.4.4 |  | 75 mm dia x 45º | No. | 2
4J.4.5 |  | 75 mm dia x 22.5º | No. | 4
4J.4.6 |  | 75 mm dia x 11.25º | No. | 5
Reducers class 16 for
4J.4.12 |  | 110mm x 75mm Reducer | No. | 1
Equal Tee class 12 for
4J.4.14 |  | Connection into existing reservoir | Sum | 1
Total Carried Forward
Brought forward
| SANS 1200L PSL 8.2 | VALVES
| 8.2.3 | Supply, deliver, install and fix in place to suit, right hand closing, non rising spindle
4J.5 |  | Air Valve (pipework excl. chamber drg. ADM/WSA 1/49/01-RO-3)
| 8.2.3 | Installed on uPVC 75mm dia pipe Flange Drilling Table 16, double
acting class 12 (Type 3)
4J.5.8 |  | 1) 25 mm diam double acting Variant Air Valve (or similar approved) | No. | 1
4J.5.9 |  | 2) 25 mm ss ball valve | No. | 1
4J.5.10 |  | 3) 500mm x 25mm diam. GMS riser, one end threaded, the other welded to flange with hole cut for riser pipe) | No. | 1
4J.5.11 |  | 4) 75mm diam. GMS flanged distance piece, length 950mm. |  | 2
4J.5.12 |  | 5) 75mm diam. GMS equal tee flanged | No. | 1
4J.5.13 |  | 6) 75mm diam. SG Iron Flange Adaptor to suit PVC | No. | 2
4J.5.14 |  | 7) 110 diam. Class 9 uPVC drainage pipe to daylight | m | 3
| 8.2.3 | For scour take-offs to 75mm diam. uPVC (all fittings, pipes and
valves) to PN 12 (Type 3)
4J.6.10 |  | 2) 75mm diam. uPVC SG Iron flange adaptor | No. | 4
4J.6.11 |  | 3) 1120mm long x 65mm diam. GMS, flanged | No. | 2
4J.6.12 |  | 4) 65mm diam. x 50mm flanged GMS reducing tee | No. | 2
4J.6.13 |  | 5) 50mm diam. flanged waterworks gate valve, to DWAF specifications, clockwise closing with cap top. | No. | 2
4J.6.14 |  | 6) 1060mm Long x 50mm diam. GMS pipe, flanged | No. | 2
4J.6.15 |  | 7) 50mm diam. x 45 degree flanged GMS bend | No. | 2
4J.6.16 |  | 8) 50mm diam. X 1100mm long GMS pipe flanged with blank flange (length to be confirmed on site) | No. | 2
4J.6.17 |  | 9) 825mm long flanged x 50mm diam. GMS pipe, flanged | No. | 2
4J.6.18 |  | 10) 110 diam. uPVC Class 9 drainage pipe to daylight | m | 6
4J.7 | 8.2.3 | Gate Valves (pipework excl. chamber drg. ADM/WSA 1/49/03-RO-1)
75mm dia. oPVC Class 12
4J.7.4 |  | 1) 80mm Gate Valve flanged, clockwise closing, non rising spindle to DWAF specs with handwheel. | No.
2) Nil
4J.7.5 |  | 3) 80mm diam. GMS, flanged distance piece, length 1200mm. | No.
4J.7.6 |  | 4) 80mm diam. SG Iron Flange Adaptor to suit 75mm diam. uPVC | No.
4J.8 | PSA 8.10 | Anchor/Thrust blocks and Pedastals
To details and dimensions as per drawings or instruction by Engineer
4J.8.1 |  | 25 MPa/19mm concrete | m³ | 3
4J.8.2 |  | Formwork | m² | 25
4J.8.3 |  | Reinforcement | t | 0.5
Total Carried Forward
Brought forward
4J.9 | SANS 1200L 8.2.13 | CHAMBERS
4J.9.1 |  | Scour Valve chamber as per drawing ADM/WSA1/49/02-R0-3, | No. | 2
complete with thrust blocks and outlet slab, concrete and brickwork,
covers and vent pipes including excavation, blinding layer, fill, backfill and
compaction. Excluding pipework and fittings.
4J.9.2 |  | Air Valve chamber as per drawing ADM/WSA1/49/01-R0-3, complete with concrete and brickwork, covers and vent pipes, excavation, blinding layer, fill, backfill and compaction. Excluding pipework and fittings. | No. | 1
4J.9.3 |  | Gate Valve Chamber as per drawing ADM/WSA1/49/04-R0-1, complete with concrete and brickwork, covers and vent pipes, etc, including excavation, blinding layer, fill, backfill and compaction. Excluding pipework and fittings. | No.
4J.9.4 |  | Pipeline Route markers as per drawing ADM/WSA1/01/01-R0, complete, including excavation, supply, delivery, marking, installation and concrete footing. | No. | 75
TOTAL CARRIED TO SUMMARY

## 500KL RESERVOIR - SECTION 7 (hidden)
OR TAMBO DISTRICT MUNICIPALITY
Dumasi Regional Water Supply Phase 1: Contract 04 | [9 empty] | SECTION 7: 500 KL RESERVOIR
ITEM REF | PAYMENT | DESCRIPTION | UNIT | BILLED QTY | RATE | BILLED AMOUNT | PREVIOUS QTY | CURRENT QTY | TOTAL QTY | PREVIOUS AMOUNT | CURRENT AMOUNT | TOTAL AMOUNT
500 KL RESERVOIR
7 | SABS 1200C 8,2,1 | Site Clearance
7.1.1 | PSC 3,1 8.3.1,2 | Clear and grub at structure as directed by the Enginner | m² | 255 | 50 | 12750 | 0 | 226.865 | 226.865 | 0 | 11343.25 | 11343.25
7.1.2 | 8.3.1.2 | Remove topsoil to nominal depth of 200 mm prior to carrying out bulk excavation below reservoir, stockpile and maintain for further use | m² | 210 | 20 | 4200 | 0 | 226.865 | 226.865 | 0 | 4537.3 | 4537.3
7.2 | SANS 1200DB PSD | Earthwork
| 8.3.2 | Bulk Excavation
7.2.1 | 8.3.2(a) PSD 8.3.2 | Excavate in all materials to bulk excavation line (that is about 100mm above the Final Excavation Level), stockpile and maintain for backfill and dispose of remainder to approved spoil site (including shaping to be free-draining and with embankment slopes shallower than 1:3 and compacting) | m³ | 900 | 150 | 135000 | 0 | 499.103 | 499.103 | 0 | 74865.45 | 74865.45
7,2,2 | 8.3.2(b) | Excavate to reduce levels to form terrace for new reservoir, stockpile for later use and maintain for backfill and dispose of the remainder to an approved spoil site (including shaping to be free- draining and with embankment slopes shallower than 1:3 and compacting) | m³ | 100 | 150 | 15000
Extra over for :
7.2.3 |  | Intermediate material | m³ | 220 | 150 | 33000 | 0 | 0 | 0 | 0 | 0 | 0
7.2.4 |  | Hard rock excavation | m³ | 40 | 250 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
7.2.5 |  | Boulder material class A | m³ | 60 | 250 | 15000 | 0 | 0 | 0 | 0 | 0 | 0
Restricted excavations:
Excavate in all materials, and stockpile for later use and maintain for backfill and dispose of the remainder to an approved spoil site (including shaping to be free-draining and with embankment slopes shallower than 1:3 and compacting)
7.2.6 | 8.3.4 | Under floor slab for outlet pipe, scour pipe work and under floor drains | m³ | 450 | 150 | 67500 | 0 | 0 | 0 | 0 | 0 | 0
7.2.7 | 8.3.4(a) | Chambers | m³ | 20 | 150 | 3000 | 0 | 0 | 0 | 0 | 0 | 0
7.2.8 |  | Extra over for:
| 8.3.4(a) | Intermediate materials | m³ | 50 | 150 | 7500 | 0 | 0 | 0 | 0 | 0 | 0
7.2.9 |  | Hard rock excavation | m³ | 30 | 250 | 7500 | 0 | 0 | 0 | 0 | 0 | 0
Backfill:
7.2.10 |  | Backfill with material from stockpile Below ground level to 75% Mod. AASHTO | m³ | 350 | 250 | Rate Only | 0 | 0 | 0 | 0 | 0 | 0
7.2.11 |  | around structures with material from excavation | m³ | 60 | 250 | 15000 | 0 | 0 | 0 | 0 | 0 | 0
| 8.3.4 | Imported Geo-fill below floor slab as directed.
7.2.12 | 8.3.10 | Rip and recompact 150mm layer insitu material, stabilised with 2% lime and compact to 75% mod. Aashto dry density at O.M.C. below floor slab as directed by the engineer. | m² | 160 | 65 | 10400 | 0 | 0 | 0 | 0 | 0 | 0
| 8.3.4 | Imported Geo-fill below floor slab as directed.
7.2.13 | SANS 1200DA | Import, place and compact in individual layers "G5" material to form Geo-fill below floor slab as directed by the engineer. Fill to be placed in layers typically 200 mm thick when loose and compacted to 77% Modified AASHTO dry density at O.M.C. | m³ | 145 | 650 | 94250 | 0 | 0 | 0 | 0 | 0 | 0
7.2.14 |  | Import, place and compact in individual layers "G2" material to form Geo-fill below floor slab as directed by the engineer. Fill to be placed in layers typically 200 mm thick when loose and compacted to 78% Modified AASHTO dry density at O.M.C. | m³ | 62 | 650 | 40300 | 0 | 0 | 0 | 0 | 0 | 0
| 8.3.2(a) | Finishing
7.2.15 |  | Topsoil obtained from prescribed stockpile on site in grassed areas 100 mm thick | m³ | 300 | 50 | 15000 | 0 | 0 | 0 | 0 | 0 | 0
Grassing
7.2.16 | 8.3.3(b) | Grassing with sods including watering, maintaining etc for the duration of the contract | m² | 150 | 50 | 7500 | 0 | 0 | 0 | 0 | 0 | 0
7.3 |  | CONCRETE (STRUCTURE)
| SABS 1200 GA & PSG PSG 7.2.6 | UNREINFORCED CONCRETE
15 Mpa / 26mm Concrete
7.3.1 | 8.4.2 | No fines layer minimum 125 mm thick | m² | 105 | 350 | 36750 | 0 | 0 | 0 | 0 | 0 | 0
7.3.2 | 8.4.2 | Blinding layer minimum 75 mm thick | m² | 205 | 350 | 71750 | 0 | 0 | 0 | 0 | 0 | 0
| 8.4.3 | 20 Mpa / 19mm Concrete
7.3.3 |  | Mass concrete in encasing scour and outlet pipes | m³ | 3 | 3000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0
7.3.4 |  | Mass concrete in brickwork to support pipes | m³ | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0
7.3.5 |  | Mass concrete to support pipes in chambers | m³ | 4 | 3000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0
REINFORCED CONCRETE
30 Mpa / 19mm Concrete In Chambers
7.3.6 |  | Floor Slab | m³ | 1 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0
7.3.7 |  | Roof slab including manhole opening ( 600 x 600 ) and casting of manhole framework in concrete | m³ | 1 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0
| 8.4.3 | 35 Mpa / 19mm Concrete
Reservoir
7.3.8 |  | Reservoir base including kickers | m³ | 35 | 4000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
7.3.9 |  | Floor slab and column base including kickers | m³ | 30 | 4000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0
7.3.10 |  | In column including column head | m³ | 5 | 4000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0
7.3.11 | 8.2.2 | Walls | m³ | 45 | 4000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0
7.3.12 |  | Roof slab including manhole opening ( 600 x 600 ), casting of manhole framework in concrete and the ring beam | m³ | 45 | 4000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0
7.3.13 |  | BRICKWORK
7.3.14 |  | In Class II motar including brickforce every 4th course
7.3.15 |  | Construct outlet / scour chamber as per drawings to 1.785m high | m² | 13 | 1850 | 24050 | 0 | 0 | 0 | 0 | 0 | 0
7.3.16 |  | Construct flow meter chamber as per drawings to 1.785m high | m² | 18 | 1850 | 33300 | 0 | 0 | 0 | 0 | 0 | 0
| 8.2PSG 8.1.1 ;8.2.2 | FORMWORK
| 8.2.2 | Smooth Vertical to plane
Class F2 To:
7.3.17 |  | Vertical wall surfaces of reservoir | m² | 200 | 650 | 130000 | 0 | 0 | 0 | 0 | 0 | 0
7.3.18 |  | Internal walls of manhole opening in roof slab ( 600 x 600 ) | m² | 5 | 450 | 2250 | 0 | 0 | 0 | 0 | 0 | 0
7.3.19 | 8.2.5 | Sides of reservoir roof slab including external side of ring beam Narrow Widths: | m² | 20 | 450 | 9000 | 0 | 0 | 0 | 0 | 0 | 0
7.3.20 |  | Internal wall base kicker not exceeding 200 mm | m | 45 | 100 | 4500 | 0 | 0 | 0 | 0 | 0 | 0
7.3.21 |  | External wall base kicker not exceeding 200 mm | m | 45 | 100 | 4500 | 0 | 0 | 0 | 0 | 0 | 0
7.3.22 |  | Vertical sides of column bases not exceeding 250mm | m | 24 | 100 | 2400 | 0 | 0 | 0 | 0 | 0 | 0
7.3.23 |  | Sides of chamber roof slab not exceeding 100 mm high | m | 45 | 100 | 4500 | 0 | 0 | 0 | 0 | 0 | 0
7.3.24 |  | 45 degrees inclined surface at ring beam on internal side on roof slab not exceeding 200 mm high | m | 45 | 100 | 4500 | 0 | 0 | 0 | 0 | 0 | 0
7.3.25 |  | 20 x 20 mm chamfer to top of Ring beams | m | 90 | 100 | 9000 | 0 | 0 | 0 | 0 | 0 | 0
| 8.2.1 | Rough vertical narrow width
7.3.26 |  | External wall base not exceeding 250 mm | m | 45 | 120 | 5400 | 0 | 0 | 0 | 0 | 0 | 0
7.3.26 |  | Internal wall base not exceeding 250 mm | m | 40 | 120 | 4800 | 0 | 0 | 0 | 0 | 0 | 0
| 8.2.2 | Column:
7.3.28 |  | Circular column not exceeding 350 mm diameter | m | 16 | 350 | 5600 | 0 | 0 | 0 | 0 | 0 | 0
7.3.29 |  | Column head ( conical - 1200 mm to 350 mm dia. ) | No | 4 | 10000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0
Horizontal Soffits: Smooth to degree of accuracy II
7.3.30 |  | Soffit for roof slab of reservoir ( Propped at 4.3 m ) | m² | 135 | 650 | 87750 | 0 | 0 | 0 | 0 | 0 | 0
7.3.31 |  | Soffit for roof slab of chamber ( Propped at 1.785 m ) | m² | 3 | 450 | 1350 | 0 | 0 | 0 | 0 | 0 | 0
FORMWORK SUNDRIES
Box out holes or form voids in:
7.3.32 |  | 250 mm thick floor slab for 100 mm diameter outlet line to reticulation ( 250 mm x 250 mm opening ) | No | 1 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0
7.3.33 |  | 200 mm thick walls for 80 mm diameter inlet pipe ( 250 mm x 250 mm opening ) | No | 1 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0
7.3.34 | 8.3 | 200 mm thick walls for 50 mm diameter overflow ( 250 mm x 250 mm opening ) | No | 1 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0
| 8.4.4 | UNFORMED SURFACE FINISHES
Wood floated finish (to degree of accuracy II)
7.3.35 |  | Reservoir roof slab including top of ring beam and top of manhole walls | m² | 155 | 50 | 7750 | 0 | 0 | 0 | 0 | 0 | 0
7.3.36 |  | Chamber roof slab | m² | 8 | 50 | 400 | 0 | 0 | 0 | 0 | 0 | 0
7.3.37 |  | Chamber floor slab | m² | 8 | 50 | 400 | 0 | 0 | 0 | 0 | 0 | 0
7.3.38 |  | Pipe supports | m² | 6 | 50 | 400 | 0 | 0 | 0 | 0 | 0 | 0
| 8.4.4 (b) PSG .5.5.10.3 | Steel float finish
7.3.39 |  | Reservoir floor slab | m² | 95 | 65 | 6175 | 0 | 0 | 0 | 0 | 0 | 0
7.3.40 |  | Top of column base | m² | 10 | 65 | 650 | 0 | 0 | 0 | 0 | 0 | 0
7.3.41 |  | Top of reservoir walls for R1 joints | m² | 10 | 65 | 650 | 0 | 0 | 0 | 0 | 0 | 0
| 8.1.2 | REINFORCEMENT
| 8.3.1 | Mild steel bars
7.3.42 |  | (a) 8 mm | ton | 0.75 | 22000 | 16500 | 0 | 0 | 0 | 0 | 0 | 0
High - tensile steel bars
7.3.43 | 8.3.2 | (a) 10 mm | ton | 2 | 22000 | 44000 | 0 | 0 | 0 | 0 | 0 | 0
7.3.44 |  | (b) 12 mm | ton | 10 | 23000 | 230000 | 0 | 0 | 0 | 0 | 0 | 0
7.3.45 |  | (c) 16 mm | ton | 10 | 23000 | 230000 | 0 | 0 | 0 | 0 | 0 | 0
Weld Mesh
7.3.46 | 8.4 PSG 8.1.3 | High tensile welded mesh Ref 517 for chamber floor and roof slab | m² | 75 | 361.9672 | 27147.54 | 0 | 0 | 0 | 0 | 0 | 0
7.4 | SABS 1200L PSG 5.5.16 | RESERVOIR PIPEWORK
Inlet Pipework
Supply, handle, lay and install galvanised and stainless steel pipes in reservoir and precast chamber
7,4,1 |  | 80mm BALEM PISKET LEVEL CONTROL VALVE, REF. BLPV 100. WITH S/S PILOT LINE AND VALVE. Marked item 10. | No | 1 | 47500 | 47500 | 0 | 0 | 0 | 0 | 0 | 0
7.4.2 |  | 80 N.B. x 700 F/F S/S PUDDLE PIPE WITH PUDDLE FLANGE 350mm FROM ONE END. BOTH ENDS FLANGED WITH ONE END OF FLANGE TO SUIT FLANGE ON ITEM No.10. Marked item 11. | No | 1 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0
7.4.3 |  | 80 N.B S/S 70°, MEDIUM. RADIUS BEND, FLANGED. Marked item 12. | No | 2 | 12000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0
7.4.4 |  | 80 N.B. x 2 300 F/F, S/S PIPE FLANGED. Marked item 13. | No | 1 | 10400 | 10400 | 0 | 0 | 0 | 0 | 0 | 0
7.4.5 |  | Supply and fix holder bat brackets for 80 mm dia. pipes as per drawings | No | 6 | 2080 | 12480 | 0 | 0 | 0 | 0 | 0 | 0
Outlet Pipework To Reticulation
Supply, handle, lay and install galvanised and stainless steel pipes in reservoir and precast chamber
7.4.6 |  | 150 Nb X 200nb X150mm S/S Bellmouth, Welded To 150 N.B X 1150mm S\S Straight Piece With Puddle Flange 455mm From Plain End. Refered To As Item 01. (Welded To Item No. 02) | No | 1 | 23950 | 23950 | 0 | 0 | 0 | 0 | 0 | 0
Welded To 150 N,B 1150mm S\S Straight
Piece With Puddle Flange 455mm From Plain End . Refered To As Item 01.(Welded To Item No. 02)
7.4.7 |  | 150 N.B S/S 90°, Medium Radius Bend, Plain Ended. Refered To As Item 08. (Welded To Item No. 03) | No | 1 | 23950 | 23950 | 0 | 0 | 0 | 0 | 0 | 0
7.4.8 |  | 200 N.B X 1800mm F/F, S/S. Pipe One Ended Plain Ended With The Other Flanged. Referred To As Item 03 | No | 1 | 8450 | 8450 | 0 | 0 | 0 | 0 | 0 | 0
Scour Pipework
Supply, handle, lay and install galvanised and stainless steel pipes in reservoir and precast chamber
7.4.9 |  | 150 Nb X 200nb X150mm S/S Bellmouth, Welded To 150 N.B X 575mm S\S Straight Piece, Plain End. Refered To As Item 07. (Welded To Item No. 08).
|  | Piece With Puddle Flange 455mm From Plain End . Refered To As Item 08.(Welded To Item No. 09) | No | 1 | 12560 | 12560 | 0 | 0 | 0 | 0 | 0 | 0
7.4.10 |  | 150 N.B S/S 90°, Medium Radius Bend, Plain Ended. Refered To As Item 08. (Welded To Item No. 09) | No | 1 | 8450 | 8450 | 0 | 0 | 0 | 0 | 0 | 0
7.4.11 |  | 150 N.B. X 4 800 F/F S/S Straight Piece, With One End Plain Ended And The Other Flanged. Refered To As Item 09. | No | 1 | 20800 | 20800 | 0 | 0 | 0 | 0 | 0 | 0
Overflow Pipework
Supply, handle, lay and install galvanised and uPVC pipes in reservoir and chamber
7.4.12 |  | 200 N.B X 285mm X 200mm S/S Bellmouth, Welded To 200 N.B X 4750mm S/S Straight Piece, Both Ends Plain Ended. Referred To As Item 04. (Welded To Item No. 05) | No | 1 | 29000 | 29000 | 0 | 0 | 0 | 0 | 0 | 0
7.4.13 |  | 200 N.B S/S 70°, Medium Radius Bend, Plained Ended.(Welded To Item No. 06). Referred To As Item 05. | No | 1 | 11360 | 11360 | 0 | 0 | 0 | 0 | 0 | 0
7.4.14 |  | 200 N.B x 1600mm F/F, S/S. PIPE PLAIN ENDED. REFERRED TO AS ITEM 06. | No | 1 | 16200 | 16200 | 0 | 0 | 0 | 0 | 0 | 0
7.4.15 |  | ROOF DRAINAGE
7.4.16 |  | 250 mm long x 75 mm diameter Class 4 uPVC pipe cast into concrete up stand beam with one end fitted with bird mesh and tightly clamped with jubilee clamps | No | 2 | 45 | 90 | 0 | 0 | 0 | 0 | 0 | 0
7.4.17 |  | 75 mm x 3800 F / F Class 4 uPVC pipe | No | 2 | 260 | 520 | 0 | 0 | 0 | 0 | 0 | 0
Extra over items for 5.5.1 and 5.5.2
7.4.18 |  | 75 mm x 70o uPVC coupling | No | 2 | 160 | 320 | 0 | 0 | 0 | 0 | 0 | 0
7.4.19 |  | 75 mm shoe | No | 2 | 260 | 520 | 0 | 0 | 0 | 0 | 0 | 0
7.5 |  | SUNDRIES
7.6 | 8.5 PSG 3.11.2 PSG 5.5.7 PSG 8.5 | JOINTS
Including all materials, formwork, water bars, sealants, bandages, etc
Construction joint in reservoir wall as detailed
7.6.1 |  | Reference Type W1& W2 | m | 25 | 2000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0
Construction joint in reservoir floor slab as detailed
7.6.2 |  | Reference Type F1 | m | 30 | 1200 | 36000 | 0 | 0 | 0 | 0 | 0 | 0
| PSG 8.18 | Construction joint between top of wall and roof slab of reservoir as detailed
7.6.3 |  | Reference Type R1 | m | 12 | 1200 | 14400 | 0 | 0 | 0 | 0 | 0 | 0
| PSG 7.2.5 PSG 8.15 | TESTING
7.6.4 |  | Testing of reservoir for Water Tightness in accordance with the specification | Sum | 1 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0
7.6.5 |  | Sterilising of reservoir in accordance with the specification | Sum | 1 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0
7.6.6 |  | STONE - RESERVOIR ROOF
7.6.7 |  | 19mm washed aggregate to top of reservoir as indicated | m³ | 175 | 850 | 148750 | 0 | 0 | 0 | 0 | 0 | 0
7.6.8 |  | SUB SOIL DRAINS
7.6.9 |  | Supply and lay A4 Bidum in trench including 250mm overlap as per the drawings | m² | 65 | 250 | 16250 | 0 | 0 | 0 | 0 | 0 | 0
7.6.10 |  | Supply and lay 6mm washed stone in trench as per drawings | m³ | 20 | 850 | 17000 | 0 | 0 | 0 | 0 | 0 | 0
7.6.11 |  | Supply and lay 70 mm " Cordrain " slotted pipe | m | 30 | 250 | 7500 | 0 | 0 | 0 | 0 | 0 | 0
7.6.12 |  | Supply and lay 70 mm solid pipe to scour chamber | m | 15 | 250 | 7500 | 0 | 0 | 0 | 0 | 0 | 0
7.7 | SABS 1200 HA PSG 8.16 | MANHOLE COVER AND FRAME
7.7.1 |  | all as detailed on drawings with frame anchors all as detailed on drawings with frame anchors cast into and frame bolted to concrete slab with galvanised bolts as specified | No | 3 | 12500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0
PRECAST MANHOLE
7.7.2 |  | Supply and construct precast concrete manhole, 750 mm diameter on inlet line complete with 15Mpa mass concrete base, light duty cover and frame to a height of 1.0m | No | 2 | 40000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0
| 8.3.3 | Access Ladders
Stainless steel access ladder fabricated to details on Drawing and fixed to inner face of reservoir and floor with M16 stainless steel Hilti H.K.B Kwik-bolts 100 mm in length. Rate to include 50x8 stainless steel flat cage hoops
7.7.3 |  | Overall length 3.75m long | No | 1 | 65000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0
7.7.4 | 8.3.2 | 700mm Galvanised handrail fabricated to details on Drawing and fixed to reservoir roof slab with M12 galvanised steel Hilti H.K.B Kwik-bolts 100 mm in length | No | 1 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0
7.8 | SABS 1200 H | FENCING
7.8.1 |  | Supply and install 2.1m HIGH x 3mm high density welded ripper razor meshed fence with 500mm dia. "flatwrap" fencing around the reservoir as illustrated on drawings. Rate to Include corner, straining and intermediate posts and all materials necessary(3 quotes form local contractors to be arranged) | m | 96 | 300 | 28800 | 0 | 0 | 0 | 0 | 0 | 0
7.8.2 |  | Supply and install 2.1m HIGH x 3mm high density welded ripper razor x 6m wide meshed driveway gatefence as illustrated on drawings. Rate to Include gate posts and all materials necessary. (3 quotes form local contractors to be arranged) | No | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.8.3 | PSA 8.8.7 | Contractor to provide "Construction Record" Information | Sum | 1 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0
Total Carried Forward To Summary | [5 empty] | 0 |  |  |  | 0 | 90746 | 90746

## SUB-CONTRACTOR'S SCOPE- SEC 8 (hidden)
OR TAMBO DISTRICT MUNICIPALITY
Dumasi Regional Water Supply Phase 1: Contract 04 | [9 empty] | SECTION 8: SUBCONTRACTORS SCOPE
ITEM REF | PAYMENT | DESCRIPTION | UNIT | BILLED QTY | RATE | BILLED AMOUNT | PREVIOUS QTY | CURRENT QTY | TOTAL QTY | PREVIOUS AMOUNT | CURRENT AMOUNT | TOTAL AMOUNT
8 |  | SUBCONTRACTOR'S SCOPE
8.1 | C3.3.2.1 | Scope of mandatory subcontract works | Sum | 1 | 9082000 | 9082000 |  | 0 | 0 | 0 | 0 | 0
Total Carried Forward To Summary | [5 empty] | 0 |  |  |  | 0 | 0 | 0